## Introduction
BWSR has created three templates (see the following tabs) to serve as a reference and a tool for your planning group as you construct your implementation schedule. The templates are not a required format; they simply show the minimum requirements for your implementation schedule. Your group is welcome to add elements to any of the templates, or create an entirely new format that better suits your watershed and your plan.
For more information, please see "Constructing a Targeted Implementation Schedule" on the BWSR website and in the One Watershed, One Plan Planning Guidebook.
One Watershed, One Plan
Implementation Schedule Sample Spreadsheet
Supporting information for Section III.E of the 1W1P Plan Content Requirements

## Organized by priority issue
Priority Issue: Flooding is causing damage to homes and businesses located near the river. |  |  |  | Measurable goal: Reduce peak flow at Northville by 30% over 10 years.
Location | Implementation Action | Measurable output for this location | Metric/Indicator | Timeframe |  |  |  |  | Estimated Cost | Estimated local contribution | Lead LGU | Supporting Entities
|  |  |  | 2017-18 | 2019-20 | 2021-22 | 2023-24 | 2025-26
Raspberry Creek Subwatershed | Wetland Restoration | 497 acres restored | Acres |  | X | X | X | X | 271000 |  | Pierce County | Stark County, Pierce SWCD, Stark SWCD, DNR
| Controlled Drainage | 248 acres treated | Acres |  | X | X | X |  | 56000 |  | Pierce SWCD | NRCS, BWSR
| Diversions | 5 diversion structures | Each |  |  | X | X | X | 9500 |  | Strong River WD | Pierce SWCD, Stark SWCD
South Branch Rose River Subwatershed | Wetland Restoration | 359 acres restored | Acres | X | X | X | X |  | 209000 |  | Pierce County | Stark County, Pierce SWCD, Stark SWCD, DNR
| Controlled Drainage | 212 acres treated | Acres |  | X | X | X |  | 48000 |  | Pierce SWCD | NRCS, BWSR
| Diversions | 4 diversion structures | Each |  | X | X | X |  | 7000 |  | Strong River WD | Pierce SWCD, Stark SWCD
Watershed-wide | Define, develop, and maintain an agricultural flood prone map | Map | Each | X |  |  |  |  | 4500 |  | Stark SWCD | Pierce SWCD, Stark County, Pierce County
[7 empty] | Subtotal: |  | 605000
Priority Issue: Drinking water is at risk due to high nitrate levels and loss of recharge. |  |  |  | Measurable goal: Reduce annual nitrate load by 45% over 10 years.
Location | Implementation Action | Measurable output for this location | Metric/Indicator | Timeframe |  |  |  |  | Estimated Cost | Estimated local contribution | Lead LGU | Supporting Entities
|  |  |  | 2017-18 | 2019-20 | 2021-22 | 2023-24 | 2025-26
Raspberry Creek Subwatershed | Targeted nutrient management | 8,300 acres | Acres | X | X | X |  |  | 15000 |  | Stark SWCD | Pierce SWCD, NRCS, crop consultants, BWSR , MPCA
| Denitrifying bioreactors | 3 bioreactors | Each |  |  |  | X | X | 12000 |  | Stark SWCD | NRCS, Pierce SWCD
| Cover crops | 6,500 acres | Acres | X | X | X | X | X | 18000 |  | Pierce SWCD | Stark SWCD, NRCS, crop consultants, BWSR , MPCA
South Branch Rose River Subwatershed | Targeted nutrient management | 7,655 acres | Acres | X | X | X | X | X | 12000 |  | Stark SWCD | Pierce SWCD, NRCS, crop consultants, BWSR , MPCA
| Denitrifying bioreactors | 2 bioreactors | Each |  | X | X |  |  | 8000 |  | Stark SWCD | NRCS, Pierce SWCD
| Cover crops | 4,865 acres | Acres | X | X | X | X | X | 12000 |  | Pierce | Stark SWCD, NRCS, crop consultants, BWSR , MPCA
Watershed-wide | Update failing and deficient SSTS | 50% SSTS compliance | % compliance | X | X | X | X | X | 106000 |  | Stark County | Pierce County, Stark SWCD, Pierce SWCD, BWSR, MPCA
| Install long-term groundwater observation wells | 15 wells | # of wells |  | X | X |  |  | 36000 |  | DNR | MGS
[7 empty] | Subtotal: |  | 219000
Priority Issue: Young forest and open land alter peak flows, affecting the stability of streams and rivers. |  |  |  | Measurable goal: Implement 4 previously-completed forest stewardship plans over 10 years.
Location | Implementation Action | Measurable output for this location | Metric/Indicator | Timeframe |  |  |  |  | Estimated Cost | Estimated local contribution | Lead LGU | Supporting Entities
|  |  |  | 2017-18 | 2019-20 | 2021-22 | 2023-24 | 2025-26
Raspberry Creek Subwatershed | Increase local capacity to implement forest management plans | 20 workshops | Workshops | X | X | X | X | X | 19000 |  | Pierce SWCD | NRCS, USFS, DNR
[7 empty] | Subtotal: |  | 19000
[7 empty] | PLAN TOTAL: |  | 843000

## Organized by location
Measurable goals: | 1) Reduce peak flow at Northville by 30% over 10 years.
2) Reduce annual nitrate load by 45% over 10 years.
3) Implement 4 previously-completed forest stewardship plans over 10 years.
Location: Raspberry Creek Subwatershed (20,262 acres)
Priority Issue | Implementation Action | Measurable output for this location | Metric/Indicator | Timeframe |  |  |  |  | Estimated Cost | Estimated local contribution | Lead LGU | Supporting Entities
|  |  |  | 2017-18 | 2019-20 | 2021-22 | 2023-24 | 2025-26
Flood Damage Reduction | Wetland Restoration | 497 acres restored | Acres |  | X | X | X | X | 271000 |  | Pierce County | Stark County, Pierce SWCD, Stark SWCD, DNR
| Controlled Drainage | 248 acres treated | Acres |  | X | X | X |  | 56000 |  | Pierce SWCD | NRCS, BWSR
| Diversions | 5 diversion structures | Each |  |  | X | X | X | 9500 |  | Strong River WD | Pierce SWCD, Stark SWCD
Drinking Water Quality | Targeted nutrient management | 8,300 acres | Acres | X | X | X |  |  | 15000 |  | Stark SWCD | Pierce SWCD, NRCS, crop consultants, BWSR , MPCA
| Denitrifying bioreactors | 3 bioreactors | Each |  |  |  | X | X | 12000 |  | Stark SWCD | NRCS, Pierce SWCD
| Cover crops | 6,500 acres | Acres | X | X | X | X | X | 18000 |  | Pierce SWCD | Stark SWCD, NRCS, crop consultants, BWSR , MPCA
Timber Harvesting | Increase local capacity to implement forest management plans | 20 workshops | Workshops | X | X | X | X | X | 19000 |  | Pierce SWCD | NRCS, USFS, DNR
[7 empty] | Local Total: |  | 400500
Location: South Branch Rose River Subwatershed (17,155 acres)
Priority Issue | Implementation Action | Measurable output for this location | Metric/Indicator | Timeframe |  |  |  |  | Estimated Cost | Estimated local contribution | Lead LGU | Supporting Entities
|  |  |  | 2017-18 | 2019-20 | 2021-22 | 2023-24 | 2025-26
Flood Damage Reduction | Wetland Restoration | 359 acres restored | Acres | X | X | X | X |  | 209000 |  | Pierce County | Stark County, Pierce SWCD, Stark SWCD, DNR
| Controlled Drainage | 212 acres treated | Acres |  | X | X | X |  | 48000 |  | Pierce SWCD | NRCS, BWSR
| Diversions | 4 diversion structures | Each |  | X | X | X |  | 7000 |  | Strong River WD | Pierce SWCD, Stark SWCD
Drinking Water Quality | Targeted nutrient management | 7,655 acres | Acres | X | X | X | X | X | 12000 |  | Stark SWCD | Pierce SWCD, NRCS, crop consultants, BWSR , MPCA
| Denitrifying bioreactors | 2 bioreactors | Each |  | X | X |  |  | 8000 |  | Stark SWCD | NRCS, Pierce SWCD
| Cover crops | 4,865 acres | Acres | X | X | X | X | X | 12000 |  | Pierce | Stark SWCD, NRCS, crop consultants, BWSR , MPCA
[7 empty] | Local Total: |  | 296000
Location: Watershed-wide (667,354 acres)
Priority Issue | Implementation Action | Measurable output for this location | Metric/Indicator | Timeframe |  |  |  |  | Estimated Cost | Estimated local contribution | Lead LGU | Supporting Entities
|  |  |  | 2017-18 | 2019-20 | 2021-22 | 2023-24 | 2025-26
Flood Damage Reduction | Define, develop, and maintain an agricultural flood prone map | Map | Each | X |  |  |  |  | 4500 |  | Stark SWCD | Pierce SWCD, Stark County, Pierce County
Drinking Water | Update failing and deficient SSTS | 50% SSTS compliance | % compliance | X | X | X | X | X | 106000 |  | Stark County | Pierce County, Stark SWCD, Pierce SWCD, BWSR, MPCA
| Install long-term groundwater observation wells | 15 wells | # of wells |  | X | X |  |  | 36000 |  | DNR | MGS
[7 empty] | Local Total: |  | 146500
[7 empty] | PLAN TOTAL: |  | 843000

## Organized by action
Measurable goals: | 1) Reduce peak flow at Northville by 30% over 10 years.
2) Reduce annual nitrate load by 45% over 10 years.
3) Implement 4 previously-completed forest stewardship plans over 10 years.
Implementation Action | Priority Issue |  |  | Measurable Output for this location | Metric | Timeframe |  |  |  |  | Estimated Cost | Estimated local contribution | Lead LGU | Supporting Entities
| Minimize flooding | Drinking water | Timber harvesting
[6 empty] | 2018-19 | 2019-20 | 2021-22 | 2023-24 | 2025-26
Wetland Restoration
Raspberry Creek Subwatershed | X |  |  | 497 acres restored | Acres |  | X | X | X | X | 271000 |  | Pierce County | Stark County, Pierce SWCD, Stark SWCD, DNR
South Branch Rose River Subwatershed | X |  |  | 359 acres restored | Acres | X | X | X | X |  | 209000 |  | Pierce County | Stark County, Pierce SWCD, Stark SWCD, DNR
Controlled Drainage
Raspberry Creek Subwatershed | X |  |  | 248 acres treated | Acres |  | X | X | X |  | 56000 |  | Pierce SWCD | NRCS, BWSR
South Branch Rose River Subwatershed | X |  |  | 212 acres treated | Acres |  | X | X | X |  | 48000 |  | Pierce SWCD | NRCS, BWSR
Diversions
Raspberry Creek Subwatershed | X |  |  | 5 diversion structures | Each |  |  | X | X | X | 9500 |  | Strong River WD | Pierce SWCD, Stark SWCD
South Branch Rose River Subwatershed | X |  |  | 4 diversion structures | Each |  | X | X | X |  | 7000 |  | Strong River WD | Pierce SWCD, Stark SWCD
Targeted nutrient management
Raspberry Creek Subwatershed |  | X |  | 8,300 acres | Acres | X | X | X |  |  | 15000 |  | Stark SWCD | Pierce SWCD, NRCS, crop consultants, BWSR , MPCA
South Branch Rose River Subwatershed |  | X |  | 7,655 acres | Acres | X | X | X | X | X | 12000 |  | Stark SWCD | Pierce SWCD, NRCS, crop consultants, BWSR , MPCA
Denitrifying bioreactors
Raspberry Creek Subwatershed |  | X |  | 3 bioreactors | Each |  |  |  | X | X | 12000 |  | Stark SWCD | NRCS, Pierce SWCD
South Branch Rose River Subwatershed |  | X |  | 2 bioreactors | Each |  | X | X |  |  | 8000 |  | Stark SWCD | NRCS, Pierce SWCD
Cover crops
Raspberry Creek Subwatershed |  | X |  | 6,500 acres | Acres | X | X | X | X | X | 18000 |  | Pierce SWCD | Stark SWCD, NRCS, crop consultants, BWSR , MPCA
South Branch Rose River Subwatershed |  | X |  | 4,865 acres | Acres | X | X | X | X | X | 12000 |  | Pierce | Stark SWCD, NRCS, crop consultants, BWSR , MPCA
Increase local capacity to implement forest management plans
Raspberry Creek Subwatershed |  |  | X | 20 workshops | Workshops | X | X | X | X | X | 19000 |  | Pierce SWCD | NRCS, USFS, DNR
Define, develop, and maintain an agricultural flood prone map
Watershed Wide | X |  |  | Map | Each | X |  |  |  |  | 4500 |  | Stark SWCD | Pierce SWCD, Stark County, Pierce County
Update failing and deficient SSTS
Watershed Wide |  | X |  | 50% SSTS compliance | % compliance | X | X | X | X | X | 106000 |  | Stark County | Pierce County, Stark SWCD, Pierce SWCD, BWSR, MPCA
Install long-term groundwater observation wells
Watershed Wide |  | X |  | 15 wells | # of wells |  | X | X |  |  | 36000 |  | DNR | MGS
[9 empty] | PLAN TOTAL: |  | 843000
843000